## Slide 1
BRIEFING
DECISION DECK
# SECOND ROASTERY DECISION
Proceed with a staged
Westhaven site
Authorize phase one for an April 2027 opening, but sign only after the landlord accepts
a six-month break option and one anchor wholesale customer commits conditional
volume.
BINDING OWNER DECISION · LEASE SIGNATURE TARGET: 18 JULY 2026
DECISION DECK
Notes: The recommendation is a staged Westhaven site, not the full build and not an unconditional lease. The investment proceeds only if both demand and lease protections are secured.

## Slide 2
EXECUTIVE SUMMARY
Stage Westhaven to protect service and limit demand risk
111%
East Yard utilization in the 690
t 2027 base case
860 t
Reliable internal capacity with
staged Westhaven
€1.12m
2031 cumulative benefit
versus outsourcing
3.6 yrs
Cash payback for the staged
option
DECISION LOGIC
Confirmed demand already takes East Yard to 95% utilization. Staging supplies enough headroom for the upside case while avoiding
the full lease’s higher up-front and fixed commitment.
Source: user brief. Financial figures are fictional planning estimates.
02 / 10
Notes: The capacity problem exists even on confirmed demand, before the unsigned grocery volume is counted. Staged Westhaven provides the required headroom with better near-term value and faster payback than the full lease.

## Slide 3
Chart: 
| 2026 forecast | 2027 confirmed | 2027 base | 2027 upside
Demand | 548 | 590 | 690 | 770
East Yard runs beyond its service-safe range in 2027
DEMAND VERSUS EAST YARD THRESHOLDS · TONNES
548 t
2026 forecast
590 t
2027 confirmed
690 t
Base
770 t
Upside
90% service threshold: 558 t
Practical capacity: 620 t
95%
utilization on confirmed 2027 demand
The base case exceeds internal capacity by 70 t. The
upside case exceeds it by 150 t.
Source: user brief. Utilization and overflow are derived from supplied demand and 620 t practical capacity.
03 / 10
Notes: Service begins to deteriorate above 558 tonnes, which is 90% of East Yard’s practical capacity. Confirmed demand is already above that point, while the base and upside cases require material overflow capacity.

## Slide 4
OPTION | UP-FRONT | FIXED COST | VARIABLE EFFECT | CAPACITY | START | MAIN DRAWBACK
Stay at East Yard | €0.18m | €0.00m | No change, then +€0.74/kg overflow | 620 t | 2 mo | Misses base demand internally
Outsource overflow | €0.05m | €0.06m | +€0.74/kg outsourced | 820 t | 3 mo | Quality and supplier dependence
Full Westhaven | €1.84m | €0.62m | −€0.19/kg above 520 t | 1,050 t | 9 mo | Commits before demand is secured
Staged Westhaven | €1.16m | €0.44m | −€0.11/kg above 520 t | 860 t | 8 mo | Second fit-out above 820 t
Staged Westhaven best balances capacity, cash and commitment
Source: user brief. Financial figures are fictional planning estimates.
04 / 10
Notes: Staying put is not a complete response to the base forecast, and outsourcing carries both a cost premium and quality dependence. The full lease adds more capacity than the stated scenarios need, while staged Westhaven covers the upside case.

## Slide 5
Phase one adds 240 t and covers the upside case
CURRENT INTERNAL NETWORK
620 t
East Yard practical capacity
STAGED INTERNAL NETWORK
860 t
+240 t phase one
East Yard · 620 t
Westhaven · 240
t
90 t headroom above the 770 t upside case.
Upside demand: 770 t
MARGIN NOTE · STAGING BUYS HEADROOM, NOT SURPLUS
Source: user brief. Phase-one addition of 240 t is derived from 860 t staged capacity less 620 t East Yard capacity.
05 / 10
Notes: The staged configuration increases reliable internal capacity from 620 to 860 tonnes. That is sufficient for the 770-tonne upside case and avoids paying now for the full site’s 1,050-tonne network capacity.

## Slide 6
Chart: 
| 2029 | 2031
Staged Westhaven | 0.46 | 1.12
Full Westhaven | 0.31 | 1.39
Staging creates more near-term value and pays back sooner
CUMULATIVE CASH BENEFIT VERSUS OUTSOURCING · €M
2029
€0.46m staged · €0.31m full
2031
€1.12m staged · €1.39m full
Staged Westhaven
Full Westhaven
3.6 yrs
Staged cash payback
4.1 yrs
Full lease cash payback
The full lease overtakes staged value only by 2031, while
requiring €0.68m more up-front cash and €0.18m more
annual fixed cost.
Source: user brief. Financial figures are fictional planning estimates.
06 / 10
Notes: Staged Westhaven leads the full lease on cumulative value through 2029 and pays back six months sooner. The full lease has greater 2031 value, but only after taking materially more commitment today.

## Slide 7
The staged case depends on demand clearing the downside
DOWNSIDE
610 t in 2027
2028 demand: 645 t
−€0.18m
2031 cumulative benefit versus
outsourcing
BASE
690 t in 2027
2028 demand: 735 t
€1.12m
2031 cumulative benefit versus
outsourcing
UPSIDE
770 t in 2027
2028 demand: 835 t
€2.06m
2031 cumulative benefit versus
outsourcing
IMPLICATION
The 74 t prospective grocery customer separates much of the 690 t base forecast from confirmed demand. A conditional volume
commitment is therefore a lease-signing gate, not a commercial afterthought.
Source: user brief. Financial figures are fictional planning estimates.
07 / 10
Notes: The downside destroys €0.18 million of value relative to outsourcing, while the base and upside cases are attractive. This asymmetry is why anchor demand must be contracted before the lease is signed.

## Slide 8
Five controls make the staged opening executable
RISK
EXPOSURE
MITIGATION
STATUS
Demand
Unsigned grocery customer represents 74 t
Secure conditional volume commitment before lease
signature
GATE
Lease
Proposed term is eight years
Require six-month break if permits or anchor volume fail
GATE
Hiring
Six roles needed; benchmark is ten weeks
Start two lead-operator searches at signing
WATCH
Quality
Equipment differs from East Yard
Four-week parallel validation and 30 blinded panels
CONTROL
Launch
Three weeks contingency on a 36-week path
Protect contingency and monitor the critical path
WATCH
IF NO DECISION IS MADE
East Yard remains above the service threshold on confirmed demand, and base-case overflow shifts to outsourcing with +€0.74/kg cost, eight-week
commitments and the pilot’s quality record.
Source: user brief.
08 / 10
Notes: The first two risks are conditions precedent to signing, while the remaining three are execution controls after signing. Deferring the decision does not preserve the status quo because confirmed demand already exceeds the service-safe range.

## Slide 9
Commit up to €1.16m phase-one fit-out
Target April 2027 opening
Do not sign the lease
Retain outsourcing as the overflow alternative
Sign only when both protections are in place
GATE 1 · DEMAND
Anchor customer signs
Conditional wholesale volume
commitment secured.
GATE 2 · LEASE
Landlord accepts break
Six-month option if permits or anchor
volume fail.
IF BOTH PASS
Sign staged lease
Target: 18 July 2026. Begin eight-month
opening plan.
Both conditions satisfied
Either condition fails
Source: user brief. Financial figures are fictional planning estimates.
09 / 10
Notes: Approval today authorizes a conditional transaction, not an unconditional lease. If either gate fails, the owners should not sign and should preserve outsourcing as the overflow route.

## Slide 10
The first 90 days secure, staff and de-risk the site
WORKSTREAM
0 TO 30 DAYS
31 TO 60 DAYS
61 TO 90 DAYS
OPENING PATH
Commercial
OWNERS
Secure anchor
Conditional volume commitment
Confirm demand evidence
Maintain lease gate discipline
Lease
OWNERS
Negotiate break
Permits and anchor volume
Sign if both pass
Target 18 July 2026
Protect critical path
Three weeks contingency
People
OPERATIONS
Start lead searches
Two roles begin at signing
Build six-role team
Ten-week benchmark
Quality
OPERATIONS
Plan validation
Parallel roast protocol
Prepare cutover gate
Four weeks and 30 panels
Timing is relative to approval except for the supplied lease-signature target.
Source: user brief.
10 / 10
Notes: The first month is about satisfying the two signing gates. After signing, hiring begins immediately and the quality-validation and launch controls are embedded into the opening plan.