## Slide 1
STATUS UPDATE
YOUR BRAND
On track, two asks
Atlas Programme · May steering update. A status deck is a decision instrument, not a
diary: what moved, what we are watching, and the decisions we need while there is
still time to act. This deck is built that way — and shows you how.
CONFIDENTIAL
2026
Notes: The headline up front: we are on track overall, and I need two decisions today. Everything else in this deck is evidence for those two sentences.

## Slide 2
02 THIS PERIOD
YOUR BRAND
On track overall — the UAT slip is
contained, two decisions due today
Scope ON TRACK
Schedule WATCH
Budget ON TRACK
Risk WATCH
SHIPPED
·
Platform build passed integration test
·
Enablement wave one trained, 96%
attendance
WATCHING
·
Migration dry run waits on the vendor
decision
·
UAT start slipped two weeks; go-live still
holds
NEXT
·
Close the vendor decision, start dry run one
·
Sign off UAT scripts with the business leads
CONFIDENTIAL
02 / 16
Notes: One slide carries the whole update: the four RAG states, what shipped, what we are watching and what happens next. If you only read one slide, read this one.

## Slide 3
03 WORKSTREAMS
YOUR BRAND
Three of four workstreams green —
migration needs today’s decision
Workstream
Scope
Schedule
Budget
Risk
Trend
Platform build
→
Data migration
↓
Enablement
↑
Reporting
→
on track · watch · at risk · arrow = trend since last steering
CONFIDENTIAL
03 / 16
Notes: The board view: state per workstream and dimension, plus the trend since last steering. Each dot converts to a native colored shape, so the board stays editable in PowerPoint.

## Slide 4
04 MILESTONES
YOUR BRAND
Go-live holds at 28 Nov — UAT absorbs
the slip
Milestone
Owner
Due
Status
Design freeze
Product
14 Mar
DONE
Platform build complete
Engineering
30 Jun
ON TRACK
Migration dry run one
Data
15 Aug
AT RISK
UAT start
Business
29 Sep
SLIPPED 2 WKS
Go-live
Programme
28 Nov
HOLDS
Status at 31 May · plan of record v3.
CONFIDENTIAL
04 / 16
Notes: Milestones are commitments, so they get a real table: owner, date, state. The slip lands on UAT, not on go-live — the critical path still closes in November.

## Slide 5
05 RISKS
YOUR BRAND
Every open risk carries an owner and a
date
Risk
Impact if it lands
Mitigation
Owner
Severity
Vendor capacity in Q3
Dry run slips past August
Second vendor pre-qualified; decision
today
PMO
HIGH
Legacy data quality
Reconciliation re-work in UAT
Profiling done; cleanup sprint in June
Data lead
MEDIUM
Key-person
dependency
Integration knowledge in one
head
Pairing since May; runbook by 30 Jun
Eng.
manager
MEDIUM
Full register in the appendix pack · reviewed weekly.
CONFIDENTIAL
05 / 16
Notes: Three risks worth the room’s attention — each with its impact, the mitigation already moving, and a name. The vendor risk is the one today’s decision retires.

## Slide 6
06 DECISIONS
YOUR BRAND
Two decisions today keep November
safe
DECISION 1
Approve the migration vendor
The €80k contract closes the dry-run capacity gap; two weeks of
onboarding are already in the plan.
Decide by 7 Jun · sponsor: CFO
DECISION 2
Release one data engineer
Four weeks from Team B unblocks the reconciliation scripts
before the cleanup sprint ends.
Decide by 14 Jun · sponsor: CTO
IF EITHER SLIPS
Go-live moves a month — the workplan slide shows the path either way.
CONFIDENTIAL
06 / 16
Notes: The two asks, each with its cost, its unblocking effect, a date and a sponsor. The callout is honest about the alternative — asking early is what keeps it cheap.

## Slide 7
07 PART TWO
YOUR BRAND
PART TWO
The evidence behind the
headline
Numbers, spend, the plan, and what moves next period.
CONFIDENTIAL
07 / 16
Notes: Part two is the detail: the numbers behind the headline for anyone who wants to go deeper.

## Slide 8
08 THE NUMBERS
YOUR BRAND
The programme in three numbers
62%
Scope delivered and accepted.
€1.9m
Spent of the €2.4m budget.
11/14
Milestones hit on their original date.
Programme office, status at 31 May.
CONFIDENTIAL
08 / 16
Notes: Three numbers anchor the update: delivery, spend, and predictability. Every one traces to the tracker the PMO publishes weekly.

## Slide 9
Chart: 
| Jan | Feb | Mar | Apr | May | Jun
Planned, €m | 0.3 | 0.6 | 1 | 1.4 | 1.8 | 2.1
Actual, €m | 0.3 | 0.55 | 0.95 | 1.3 | 1.75 | 1.9
09 BUDGET
YOUR BRAND
Spend tracks plan — €0.2m under,
contingency untouched
Cumulative spend runs just under the curve; the gap is timing, not scope.
·
Forecast at completion: €2.35m
·
Contingency of €150k not drawn
·
Vendor contract adds €80k from June
Source: finance actuals to 31 May.
CONFIDENTIAL
09 / 16
Notes: Planned versus actual as two lines — the chart carries its own numbers, so it converts to a native, data-editable PowerPoint chart. The reading sits beside it: under plan on timing, forecast inside budget.

## Slide 10
10 WORKPLAN
YOUR BRAND
The plan to November on one slide
Q1
Q2
Q3
Q4
PLATFORM
BUILD
Build & integrate
DATA
MIGRATION
Dry runs & cutover
UAT
Scripts & execution
ENABLEMENT
Train the regions
GO-LIVE
Programme office · plan of record v3.
CONFIDENTIAL
10 / 16
Notes: The whole plan as swimlanes: each bar a phase with its own start and length, the go-live milestone at the end of Q4. Every bar is a movable native shape in the converted PowerPoint.

## Slide 11
11 NEXT PERIOD
YOUR BRAND
What moves before the next steering
NEXT TWO WEEKS
Close the asks
Vendor signed, engineer released, dry-run
environment ready.
BY NEXT STEERING
Dry run one
First migration dry run complete; UAT scripts
signed off.
THE QUARTER
UAT running
Business testing underway; go/no-go criteria
agreed for November.
THE FOCUS
Protect the migration critical path — everything else on the plan has slack.
CONFIDENTIAL
11 / 16
Notes: Three horizons: the fortnight, the next steering, the quarter. One focus — the migration critical path — so the room knows what to protect.

## Slide 12
12 DEPENDENCIES
YOUR BRAND
Three cross-team needs — one blocked
We need
From
By
Status
Security review slot
IT Security
20 Jun
REQUESTED
API rate-limit increase
Platform team
30 Jun
AGREED
Anonymised test data set
Finance ops
15 Jun
BLOCKED
Escalation path: programme sponsor → CIO weekly.
CONFIDENTIAL
12 / 16
Notes: Dependencies are asks of other teams, so they are named the same way: what, from whom, by when, and the honest state. The blocked one goes to the sponsor today.

## Slide 13
13 CHANGES
YOUR BRAND
Scope changes stay inside contingency
Change request
Cost
Schedule
Status
CR-11 · Drop the legacy export
−€15k
±0 weeks
APPROVED
CR-12 · French localisation
+€40k
±0 weeks
IN REVIEW
CR-13 · Extra training wave
+€20k
+1 week
DECLINED
Change board of 22 May · net approved to date: +€25k.
CONFIDENTIAL
13 / 16
Notes: Every scope change with its cost, schedule effect and decision state — and the running net, so the board sees changes stay inside contingency.

## Slide 14
14 SO WHAT
YOUR BRAND
THE HABIT
A status update is a decision
instrument, not a diary. Lead with what
changed — and ask early, because bad
news does not improve with age.
CONFIDENTIAL
14 / 16
Notes: The habit this format enforces: what changed, what it means, what we need — every period, in the same order, so the room compares like with like.

## Slide 15
15 OPEN CANVAS
YOUR BRAND
Free canvas — keep the header and footer, then
compose any layout you like in this space. Text, boxes,
inline SVG, a table or a chart all still convert to native,
editable objects.
CONFIDENTIAL
15 / 16

## Slide 16
16 CLOSE
YOUR BRAND
NEXT STEPS
Two asks on the table — next steering 25
June
The asks
Vendor approval by 7 Jun; the engineer by 14 Jun.
Between steerings
Weekly one-pager to sponsors; escalations any time.
CONFIDENTIAL
16 / 16
Notes: Two asks with dates, and the cadence between steerings. Thank you — decisions, please, before we leave the room.